## Sheet1
RACI Matrix
| Project Team Members | [5 empty] | External Resources
| Aya Hamdy[PM] | Dina | Hossam | Marwa | Maryam Mohamed | Mariam Nesim | Customer
Initiate Phase Activities
- Receive Requirement From Customer | R | A | A | A | A | A | C
- SIQ Document | C | I | R | C | I | I | A/C
Plan Phase Activities
- Create Project Plan | A/C | C | C | C | R | C | C
- Create Schedule | R | C | C | C | C | C | C
- CreateProject risk sheet | A/C | I | I | R | I | I | C
- CreateProject Issue sheet | A/C | I | I | I | I | R | A
- Create Configuration Management plan | A | I | C | I | R | I | A
- Create RACI Sheet | R | I | I | I | I | I | A
- Create CI List | A/C | I | R | I | C | I | A
- Create CCB | A/C | I | I | I | I | R | A
- Create Test plan | A/C | I | I | R | I | I | A
- Create Skill Matrix | R | I | I | I | I | I | A
Analysis phase Activities
- SRS | A/C | R | C | I | I | I | A
_ RTM | A | C | I | I | I | R | A
- SRS PR Sheet | A | C | R | I | I | C | C
Design Phase Activities
- High level design | R | I | I | C | I | I | A
- Usecase and usecase scenario | A/C | I | I | R | I | I | A
- ERD | I | C | R | I | I | I | A
- WireFrames | C | I | I | I | R | I | A
- Class Diagram | I | I | I | I | I | R | A
- DFD | A/C | R | I | I | I | I | A
Implementation Phase Activities
Frontend Foodies Add Menu page | R | I | I | I | I | I | A
Frontend Foodies user profile page | C | R | I | I | I | I | A
Frontend Foodies Admin profile page | C | R | I | I | I | I | A
Frontend Foodies delete user page | C | I | R | I | I | I | A
Frontend Foodies Home page | I | I | I | I | R | I | A
Frontend Foodies Login page | I | I | I | R | I | I | A
Frontend Foodies Offers page | I | I | I | I | R | I | A
Frontend Foodies View Menu page | C | I | R | I | I | I | A
Frontend Foodies Registration page | I | I | I | R | I | I | A
Backend Foodies All Pages | I | I | I | I | I | R
Update RACI table | R | I | I | I | I | I
Update Project Schedule | R | I | I | I | I | I
Testing Phase Activities
write and execute TC from 1-12 in SRS Requirements | I | I | R | I | I | I
write and execute TC from 13-25 in SRS Requirements | I | I | I | R | I | I
write and execute TC from 26- 37in SRS Requirements | I | I | I | I | R | I
write and execute TC from 38-50 in SRS Requirements | R | I | I | I | I | I
write and execute TC from 51-59 in SRS Requirements | I | R | I | I | I | I
fix the bugs | I | I | I | I | I | R
Deployment
Role
Project Deliverable
(or Activity)