## Sheet1
RACI Matrix
| Project Team Members | [5 empty] | External Resources
| Aya Hamdy[PM] | Dina | Hossam | Marwa | Maryam Mohamed | Mariam Nesim | Customer
Initiate Phase Activities
- Receive Requirement From Customer | R | A | A | A | A | A | C
- SIQ Document | C | I | R | C | I | I | A/C
Plan Phase Activities
- Create Project Plan | A/C | C | C | C | R | C | C
- Create Schedule | R | C | C | C | C | C | C
- CreateProject risk sheet | A/C | I | I | R | I | I | C
- CreateProject Issue sheet | A/C | I | I | I | I | R | A
- Create Configuration Management plan | A | I | C | I | R | I | A
- Create RACI Sheet | R | I | I | I | I | I | A
- Create CI List | A/C | I | R | I | C | I | A
- Create CCB | A/C | I | I | I | I | R | A
- Create Test plan | A/C | I | I | R | I | I | A
- Create Skill Matrix | R | I | I | I | I | I | A
Analysis phase Activities
- SRS | A/C | R | C | I | I | I | A
_ RTM | A | C | I | I | I | R | A
- SRS PR Sheet | A | C | R | I | I | C | C
Design Phase Activities
Implementation Phase Activities
Testing Phase Activities
Deployment
Role
Project Deliverable
(or Activity)