## Foodie_IssuesSheet_V1.1
Issues List
ID | Description | Corrective Action | Start Day | End Day | Status
Foodie_IS_001 | Sunday and Monday were holidays so we couldn't make any meetings or work | working more hours during the week | 2019-04-28 |  | Open
Foodie_IS_002 | Configuration management tool misconfiguration, lead to loss of files | re-configuring the repository using local copies of the files | 2019-05-01 | 2019-04-29 | Closed
Foodie_IS_003 | answers to the SIQ sheet that was sent by the customer came late | working more hours during the week | 2019-05-02 | 2019-05-03 | Closed
Foodie_IS_004 | Decisions made on the project lifecycle changed multiple times | several amendments to different types of documents were made | 2019-04-29 | 2019-05-02 | Closed
Foodie_IS_005 | versioning and naming conventions were not well planned | team held a meeting to decide on a naming convention | 2019-05-03 |  | Open

## Revision History
Version | Description | Author | Reviewed By
1 | Initial creation | Aya Hamdy | Maryam M.