## Revisison_History
Revised on | Version | Description | Revised by
28/4/2019 | 0 | Document Created | Marwa sheshtawy
29/4/2019 | 1 | Peer Reviewed and some comments added | Aya Hamdy
2019-02-05 | 2 | Peer Reviewed and some comments added | Aya Hamdy
2019-03-05 | 3 | All Comments implemented with some modifications | Marwa sheshtawy

## Risk_Sheet_V1
Risk ID | Risk Description | impact | Pobability | Mitigation Option | Mitigation option description | Risk Type
Foodies_Sys_Risk_001 | Delivery Timing within only 1 month | Medium | High | Mitigate | 1- Working more than 8 hours per day. 2- Working during weekends. 3- Team's workload is divided fairly | Project
Foodies_Sys_Risk_002 | Scope Change , all project work products are usually designed based on the initial project scope. Thus, any change in the project scope during execution will mean that the entire initial project plan will have to be reviewed | High | Medium | Mitigate | More time and resources will be needed as all the concerned parties need to work on the new scope or modify their previous work. | Project
Foodies_Sys_Risk_003 | Ramadan Working hours - Fasting in the summer, combined with disturbances in normal sleep pattern, can leave individuals feeling more tired than normal and potentially light headed | Medium | Medium | Accept | Accommodating flexible working hours , No need for face - to - face meetings , using Video Conferencing Apps for Virtual Meetings is enough like (Skype) or desktop sharing Apps like (Team Viewer) . | Project
Foodies_Sys_Risk_004 | Lack of backend development knowledge by most of the team | Medium | Low | Mitigate | Work on team skills development during requirement analysis and design phase | Product
Foodies_Sys_Risk_005 | WebPage gui doesn't meet customer needs | High | Medium | Mitigate | Clear Acceptance criteria must be defined , wireframes will be developed first before designing to assure that the designs meet customer expectations. | Business
Foodies_Sys_Risk_006 | Impacted individuals aren't kept informed of any changes. | Medium | Low | Avoid | all team members must be involved in any change process, all changes must be documented and uploaded to the CM tool. | Project
Foodies_Sys_Risk_007 | The Competition between teams | Low | High | Accept | try to meet deadlines as much as possible , keep the whole team motivated all the time . | Project
Foodies_Sys_Risk_008 | The cost of web hosting site | Medium | Low | Transfer | Use free web hosting for 3 months then Transfer to one of Enterprise track to get the best web hosting services . | Business
Foodies_Sys_Risk_009 | Integration of tasks | High | Medium | Mitigate | daily meeting ( not necessarily face to face meeting) to integrate and communicate the tasks done by each team member at the end of the day | Product
Foodies_Sys_Risk_010 | Delays of stakeholder approvals impact the project | Medium | High | Avoid | By sending to stakeholder as early as possible and send questions with proposed solution to facilitate the speed answering . | Business

## Risk_Sheet_PR
RISK ID | Revised on | Version | Description | Notes | Reviewed By
Risk_004 | 29/4/2019 | 1.1 | Lack of JavaScript, bootstrap knowledge by most of the team | * Lack of development knowledge by most of the team | Aya Hamdy
Risk_004 | 29/4/2019 | 1.1 | Work on developing the team skills during requirement analysis and design phase . | * Work on team skills development during requirement analysis and design phase . | Aya Hamdy
Risk_006 | 29/4/2019 | 1.1 | all team members must be involved in change process and any and all changes must be documented and uploaded to the CM tool. | * all team members must be involved in any change process, all changes must be documented and uploaded to the CM tool. | Aya Hamdy
Risk_007 | 2019-02-05 | 1.2 | Use free web hosting for 3 months then Transfer to one of Enterprise track to get the best web hosting services . | * I think as a learning project 3 months is enough for free hosting, if we host our web application | Aya Hamdy
Risk_009 | 2019-02-05 | 1.2 | Integration of tasks | * this is a high impact because our lack of development with web backend languages, so the integration will be high risky to our team | Aya Hamdy
Risk_010 | 2019-02-05 | 1.2 | Integration of tasks | * duplicate with Risk_009 | Aya Hamdy
Risk_011 | 2019-02-05 | 1.2 | Delays to stakeholder approvals impact the project | * I think it has a high impact beacuase we send to our customer early and he delay with the answer | Aya Hamdy
All Risks | 2019-02-05 | 1.2 |  | ALL risks shoud be prioritized. | Aya Hamdy