## Sheet1
DR_ID | Decription | Precondition | Steps to Reproduce | Test Data | Expected Result | Actual Result | Severity | Priority | Type | Status | Assigned to | Tester Name | Attachments | TC_ID | Opened Date | Closed Date
Foodies_SRS_052_D001 | Cancel Button Clear reasult of searching about user | Register with valid Admin account credientials | 1- Navigate to Login page using URL in testData. 2- Enter Valid data in all fields ( use testData). 3- Click on "Login". 4- Press Delete User 5- write "Dina" in search 6- Click on "Cancel" button | UserName : DDdd Password : DDdd12@@ url:http://localhost:81/foodies/Foodies_FrontEnd_LoginPage.php Broswer : chrome Version 74.0.3729.157 | cancel button will clear result of searching about users | Cancel Button doesn't work | High | High | Functional | Fixed | Mariam Nessim | Dina Ibrahim |  | Foodies_SRS_052_T004
Foodies_SRS_052_D002 | verify when admin clicks on submit button to add new restaurant with valid data, system shall display message says “restaurant added successfully | Register with valid Admin account credientials | 1- Navigate to Login page using URL in testData. 2- Enter Valid data in all fields ( use testData). 3- Click on "Login". 4- Press "Add Restaurant" 5-Press "Submit" button | UserName : DDdd Password : DDdd12@@ url:http://localhost:81/foodies/Foodies_FrontEnd_LoginPage.php Broswer : chrome Version 74.0.3729.157 | when admin clicks on submit button to add new restaurant with valid data, system shall display message says “restaurant added successfully | Message doesn't display | Low | Mediuem | Functional | Rejected - it's working as expected result | Mariam Nessim | Dina Ibrahim |  | Foodies_SRS_053_T005
Foodies_SRS_052_D003 | Message Displayed "user deleted successfully" after the admin delete the user | Register with valid Admin account credientials | 1- Navigate to Login page using URL in testData. 2- Enter Valid data in all fields ( use testData). 3- Click on "Login". 4- Press Delete User 5- write "Dina" in search 6- Click on "Delete" button | UserName : DDdd Password : DDdd12@@ url:http://localhost:81/foodies/Foodies_FrontEnd_LoginPage.php Broswer : chrome Version 74.0.3729.157 | system shall display message says “user deleted successfully”. | I don't recive any message to know this user deleted successuffely or not | Low | Mediuem | Functional | Fixed | Mariam Nessim | Dina Ibrahim |  | Foodies_SRS_054_T006
Foodies_SRS_052_D004 | Verify order button will display Popup message “phone number of restaurant and congratulation you have one order free” If this was his fifth order | Add New User with valid user account credientials | 1- Navigate to Login page using URL in testData. 2- Enter Valid data in all fields ( use testData). 3- Click on "Login" Button 4- press "Ok" on Popup message 5- go to search and write "KFC" then press search 6- press "Menu" Button 7- press "Order" Button then Press"OK" 8- press "Order" Button then Press"OK" 9- press "Order" Button then Press"OK" 10- press "Order" Button then Press"OK" 11- press "Order" Button then Press"OK" 12- press "Order" Button then Press"OK" | UserName : Dina Password : DDdd12@@ url:http://localhost:81/foodies/Foodies_FrontEnd_LoginPage.php Broswer : chrome Version 74.0.3729.157 | order button will display Popup message “phone number of restaurant and congratulation you have one order free” If this was his fifth order | shall be get this message in 6th order but I get it on 7th order | High | Mediuem | Functional | Fixed | Mariam Nessim | Dina Ibrahim |  | Foodies_SRS_057_T009
Foodies_SRS_052_D005 | The "Previous Button" is not dimmed in case of Displaying the first 5 nearby Restaurants. | Login with valid user credientials | 1- Navigate to Login page using URL in testData. 2- Enter Valid Data (testData). 3- Click on "Login" Button. 4- Click Ok on pop-up message to allow accesssing your location. 5- Click on "Previous" button. | UserName : Mariam Password : MMmm12@@ url:"http://localhost:81/foodies/Foodies_FrontEnd_LoginPage.php" Broswer : chrome Version 74.0.3729.157 | Previous button is not-clickable. | Previous Button is click-able | Low | Low | Functional | Rejected - it doesn't map to any srs | Mariam Nessiem | Marwa El-sheshtawy |  |  | 22/5/2019
Foodies_SRS_052_D006 | The "Next Button" is not dimmed in case of Displaying the last 5 or less nearby Restaurants. | Login with valid user credientials | 1- Navigate to Login page using URL in testData. 2- Enter Valid Data (testData). 3- Click on "Login" Button. 4- Click Ok on pop-up message to allow accesssing your location. 5- Click on "Next" button until you reach the last restaurants page. 6- Click"Next" button on the last 5 or less restaurants page. | UserName : Mariam Password : MMmm12@@ url:"http://localhost:81/foodies/Foodies_FrontEnd_LoginPage.php" Broswer : chrome Version 74.0.3729.157 | Next button is not-clickable. | Next Button is click-able | Low | Low | Functional | Rejected - it doesn't map to any srs | Mariam Nessiem | Marwa El-sheshtawy |  |  | 22/5/2019
Foodies_SRS_052_D007 | System Failed to display a "Pop-up message" in case of no nearby Restaurants to the user's location. | 1- Login with valid user credientials. 2- No restaurants for user's location in database. | 1- Navigate to Login page using URL in testData. 2- Enter Valid data in all fields ( use testData). 3- Click on "Login"button. 4- Click on on pop-up message to enable accessing user's location. | UserName : Mariam Password : MMmm12@@ url:"http://localhost:81/foodies/Foodies_FrontEnd_LoginPage.php" Broswer : chrome Version 74.0.3729.157 | Popup Message appears to the user | No Pop-up Message appeared | High | High | Functional | Fixed | Mariam Nessiem | Marwa El-sheshtawy |  |  | 22/5/2019
Foodies_SRS_052_D008 | System Failed to display a pop-up message text is the required text to appear | 1- Login with valid user credientials. 2- No restaurants for user's location in database. | 1- Navigate to Login page using URL in testData. 2- Enter Valid data in all fields ( use testData). 3- Click on "Login"button. 4- Click on on message to enable accessing user's location. | UserName : Mariam Password : MMmm12@@ url:"http://localhost:81/foodies/Foodies_FrontEnd_LoginPage.php" Broswer : chrome Version 74.0.3729.158 | message text is "There is no near Restaurants from you :( " | No Message appeared | High | High | UI | Fixed | Mariam Nessiem | Marwa El-sheshtawy |  |  | 22/5/2019
Foodies_SRS_052_D009 | User can't search for restaurant by substring of restaurant's name. | 1- Login with valid user credientials . 2- There'a a restaurant that conatin the substring already exit in database. | 1- Navigate to Login page using URL in testData. 2- Enter Valid data in all fields ( use testData). 3- Click on "Login"button. 4- Click on on pop-up message to enable accessing user's location. 5- Write Part of restaurant's name ( use test data) 6- Click on "Search Button" | UserName : Mariam Password : MMmm12@@ url:"http://localhost:81/foodies/Foodies_FrontEnd_LoginPage.php" Broswer : chrome Version 74.0.3729.169 Substring of restaurant's name : "kf" | Restaurants that contains the substring in it's name appeared | No Restaurant Displayed. | High | High |  | Fixed | Mariam Nessiem | Marwa El-sheshtawy |  |  | 22/5/2019
Foodies_SRS_052_D010 | Add resturant already exists | 1- Login with valid Admin credientials . | 1- Navigate to Admin Add resturant page url:"http://localhost:8081/foodies/Development/foodies/Foodies_FrontEnd_AddMenu.php" 2- add valid data 3- Click on "Submit" button | UserName : DDdd Password : DDdd12@@ Resturant Name:Chicken Fila Resturant Phone: +2025646999 location: cairo Restaurant promotion : onion rings for 2 SW item1: juicy juily price:49 Item2:original price:45 Item3:maxicano price: 95 Item4:american price:100 Item5:Grilled price:85 | meassage displayed says "this restaurant already added before" | Add resturant already added before | Mediuem | High | Functional | Rejected - it's working as expected result | Mariam Nesiem | Aya Hamdy |  | SRS040_TC004 | 24/5/2019
Foodies_SRS_052_D011 | popup message is displayed with error instead of red text message when enter invalid user id | 1- Login with valid Admin credientials . | 1- Navigate to create Account page url:"http://localhost:8081/foodies/Development/foodies/Fooides_FrontEnd_Register.php" 2- Enter invalid userId and valid Email and Password 3- Click on "Register" button | UserID: Aya Email: aya@gmail.com password:Aya@1234 | red text message is displaied next to user id field says "Invalid username or password" | popup message is displayed with error instead of red text message | Low | Low | Functional | Rejected - it doesn't map to any srs | Mariam Nesiem | Aya Hamdy |  | SRS045_TC009 | 24/5/2019
Foodies_SRS_052_D012 | the error message is displayed above the fileds not next to it when enter invalid data . | 1- Registered Admin / User 2- Browser: Chrome | 1- Navigate to login page url:"http://localhost:8081/foodies/Development/foodies/Foodies_FrontEnd_LoginPage.php" 2- Enter invalid password 3- Click on "Login" button | UserID:AyaHamdy password:123456 | red text message is displaied next to password field says "Invalid username or password" | the message is displayed above the filed not next to it. | Low | Low | Functional | Rejected - it doesn't map to any srs | Mariam Nesiem | Aya Hamdy |  | SRS046_TC010 | 24/5/2019
Foodies_SRS_052_D013 | The Error message for adding UserID already exist | 1- Use chrome browser 2- Open this url " http://localhost:81/foodies/Foodies_FrontEnd_LoginPage.php " 3- Click on Register here Button | 1- Enter Valid Email 2- Enter UserID 3- Enter Valid Password 4- Enter matching Confirmation Password 5- Select the Gender 6- Select the Location 7- Click on button Register | 1- Email "ahmed@gmail.com" 2- UserID "222222" 3- Password "Ahmed@m123*" 4- Confirmation Password "Ahmed@m123*" 5- Gender "Male" 6- Location "Cairo" | Red message appears with "please write another ID" | Red message appears with " The userID already exist" | Low | Low | Functional | Closed | Mariam Nesiem | Hossam Galal |  | Foodies_TC_003 | 24/5/2019 | 24/5/2019
Foodies_SRS_052_D014 | validate that "Offers & Promotions Screen" lists all restaurants that have promotions and offers | Logged-in user with a location that have restaurants with offers | 1- Navigate to User homepage url:"http://localhost:81/foodies/Foodies_FrontEnd_Homepage.php" 2- Click on "Go to Restaurants with offers" button 3- Click on "Menu" button next to the restaurant name |  | - User is able to identify the restaurant with an offer - 'take one free' is displayed in the menu page | - User isn't able to identify the restaurant with an offer - 'take one free' isn't displayed in the menu page | High | High | Functional | Fixed | Mariam Nesiem | Maryam mohamed |  | Foodies_TC_050 | 24/5/2019
Foodies_SRS_052_D015 | Validate that every 5 orders the user will get one order free | Logged-in user with no previous orders | 1- Navigate to User homepage url:"http://localhost:81/foodies/Foodies_FrontEnd_Homepage.php" 2- Click on "Menu" button next to the restaurant name 3- Click on "Order" Button and press "Ok" when the pop-up message appears 4- Repeat step 3 for 5 more times (Total 6 orders) |  | - "0" is displayed in the free orders section in the "User Account" Page - "Loyalty points" bar is restored to empty (0%) | - "1" is displayed in the free orders section in the "User Account" Page - "Loyalty points" bar is restored to empty (0%) | High | High | Functional | fixed | Mariam Nesiem | Maryam mohamed |  |  | 24/5/2019
Foodies_SRS_052_D016 | Validate that every 5 orders the user will get one order free | Logged-in user with no previous orders | 1- Navigate to User homepage url:"http://localhost:81/foodies/Foodies_FrontEnd_Homepage.php" 2- Click on "Menu" button next to the restaurant name 3- Click on "Order" Button and press "Ok" when the pop-up message appears 4- Repeat step 3 for 10 more times (Total 11 orders) |  | - "1" is displayed in the free orders section in the "User Account" Page - "Loyalty points" bar filled (100%) | - "2" is displayed in the free orders section in the "User Account" Page - "Loyalty points" bar filled (20%) | High | High | Functional | Fixed | Mariam Nesiem | Maryam mohamed |  |  | 24/5/2019
Foodies_SRS_052_D017 | Validate that User Account Page shall display how many free orders this user made in case of 0 orders | 1- Logged-in user 2- Browser: Chrome 3- User have 0 free orders | 1- Navigate to user account page 2- Observe |  | "free orders" label in the user account page display 0 |  | High | High | Functional | Need information | Mariam Nesiem | Maryam mohamed |  |  | 24/5/2019
Foodies_SRS_052_D018 | Validate that User Account Page shall display how many free orders this user made in case of 1 order | 1- Logged-in user 2- Browser: Chrome 3- User have 1 free order | 1- Navigate to user account page 2- Observe |  | "free orders" label in the user account page display 1 |  | High | High | Functional | Need information | Mariam Nesiem | Maryam mohamed
Foodies_SRS_052_D019 | validate that when user click on "confirm order" button, loyalty points will increase by one for each order, unless it’s a free order | 1- Logged-in user 2- Browser: Chrome 3- User have 1 free order | 1- Navigate to User homepage url:"http://localhost:81/foodies/Foodies_FrontEnd_Homepage.php" 2- Click on "Menu" button next to the restaurant name 3- Click on "Order" Button and press "Ok" when the pop-up message appears 4- Click on the "User Account Page" button in the navbar |  | - "Loyalty points" doesn't change | - "Loyalty points" changed | High | High | Functional | Rejected - it's working as expected result | Mariam Nesiem | Maryam mohamed
Foodies_SRS_052_D020 | Validate that "Delete User" page controlled by Admin only (Accessing page with regular user credentials) | 1- Logged-in user (NOT ADMIN) 2- Browser: Chrome | 1- Navigate to admin account page "http://localhost:81/foodies/Foodies_FrontEnd_AdminProfile.php" 2- Click on "Delete User" Button (if Applicable) | Regular User Valid Credentials UserName: Mariam Password : MMmm12@@ | - User is redirected to homepage | user can click on delete user and react as an admin | High | High | Functional | Fixed | Mariam Nesiem | Maryam mohamed

## Sheet2
New
Open
Closed
Rejected
Fixed