## RTM
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## SRS
ID | SRS-ID | Document Version | Notes | Reviewer Name | publisher notes
Foodies_PR_001 | Foodies_SRS_003 | V1.2 | this requirment doesn't match to any CRS , it's assumtion | Hossam Galal | It's not assumtion
Foodies_PR_002 | Foodies_SRS_005 | V1.2 | the system's language shall accept english and franko | Hossam Galal | done
Foodies_PR_003 | Foodies_SRS_008 | V1.2 | this requirment is dublicated referring to Foodies_SRS_001 | Hossam Galal | done
Foodies_PR_004 | Foodies_SRS_009 | V1.2 | strong password replied 2 times . strong password shall be :- "not should" 1- 2 Capital letters . 2- 2 Special Characters . 3- it's length Minimum [8] character Maximum [10] character . "not his" | Hossam Galal | done
Foodies_PR_005 | Foodies_SRS_010 | V1.2 | this requirment doesn't match to any CRS , it's assumtion | Hossam Galal | it's standard
Foodies_PR_006 | Foodies_SRS_011 | V1.2 | please specify which model you are "registeration or login screen" | Hossam Galal | done
Foodies_PR_007 | Foodies_SRS_012 | V1.2 | please specify which model you are "registeration or login screen" | Hossam Galal | done
Foodies_PR_008 | Foodies_SRS_013 | V1.2 | If the user press login without filling the email & Password fields the system behaviour shall do nothing | Hossam Galal | done
Foodies_PR_009 | Foodies_SRS_014 | V1.2 | the confirmation password field shall match the password field | Hossam Galal | done
Foodies_PR_010 | Foodies_SRS_016 | V1.2 | this requirment is dublicated | Hossam Galal | its's not dup. It's explained what the register now link do
Foodies_PR_011 | Foodies_SRS_017 | V1.2 | please specify which page you are ! | Hossam Galal | done
Foodies_PR_012 | Foodies_SRS_018 | V1.2 | the user can accept or reject the system access for the user location | Hossam Galal | done
Foodies_PR_013 | Foodies_SRS_019 | V1.2 | after the user press the login page the system shall navigate to the home page | Hossam Galal | done
Foodies_PR_014 | Foodies_SRS_021 | V1.2 | The system should get customer location in range of 5KM away from restaurants | Hossam Galal | done
Foodies_PR_015 | Foodies_SRS_022 | V1.2 | The Nearby 5 restaurants shall be sorted alphabetical | Hossam Galal | done
Foodies_PR_016 | Foodies_SRS_023 | V1.2 | language mistake "restaurants should contains" should be "restaurants shall contain" | Mariam Nesiem | done
Foodies_PR_017 | Foodies_SRS_024 | V1.2 | SRS should be Compatible with SIQ_012 | Mariam Nesiem | done
Foodies_PR_018 | Foodies_SRS_033 | V1.2 | SRS should be Compatible with SIQ_015 | Mariam Nesiem | done
Foodies_PR_019 | Foodies_SRS_034 | V1.2 | this requirment is dublicated referring to Foodies_SRS_033 | Mariam Nesiem | it's not a duplicate
Foodies_PR_020 | Foodies_SRS_036 | V1.2 | this requirment doesn't match to any CRS , it's assumtion | Mariam Nesiem | i found this in description of the project by customer
Foodies_PR_021 | Foodies_SRS_037 | V1.2 | this requirment doesn't match to any CRS , it's assumtion | Mariam Nesiem | i found this in description of the project by customer
Foodies_PR_022 | Foodies_SRS_038 | V1.2 | this requirment doesn't match to any CRS , it's assumtion | Mariam Nesiem | you can ask in SIQ
Foodies_PR_023 | Foodies_SRS_041 | V1.2 | SRS should be Compatible with SIQ_017 | Mariam Nesiem | it's completely different
| Foodies_SRS_042 | V1.2 | this SRS should ddivided to two SRS | Mariam Nesiem | done
Foodies_PR_024 | Foodies_SRS_044 | V1.2 | this requirment is dublicated referring to Foodies_SRS_043 | Mariam Nesiem | it's completely different
Foodies_PR_025 | Foodies_SRS_001 | v1.7 | replace submit button with create account button | Aya hamdy | done
Foodies_PR_026 | Foodies_SRS_042 | v1.7 | replace submit button with create account button | Aya hamdy | done
Foodies_PR_027 | Foodies_SRS_* | v1.7 | Edit all English and grammer mistakes | Aya hamdy | done
Foodies_PR_028 | Foodies_SRS_043 | v1.7 | redundant with Foodies_SRS_025 | Aya hamdy | it's completely different

## SIQ
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## RiskSheet
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## RACI
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes
Foodies_RACI_001 | RACI | 1.4 | All tasks should be documented | Aya Hamdy | done for implementation phase

## CRS
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CMP
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CI List
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## TestPlan
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## PP
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes
Foodies_PP_001 | Foodies_PP | 3 | Please update project team section 4.4.1 As Raci Table | Aya Hamdy

## CCB
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CR
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## DefectReport
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## TestCaseReport
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## IssuesList
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## SDD
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes
PR_SDD_001 | Foodies_Sys_UseCase_001 | 1.5 | confirmation password is missing at steps number 2 | Mariam Nesiem
PR_SDD_002 | Foodies_Sys_UseCase_001 | 1.5 | step number 4 from steps : system should return to home page not login page | Mariam Nesiem
PR_SDD_003 | Foodies_Sys_UseCase_002 | 1.5 | step number 3.1 from steps : if user is an admin should be redirected to admin panel not profiles page | Mariam Nesiem
PR_SDD_004 | Foodies_Sys_UseCase_003 | 1.5 | step number 1 from steps : user can show loyalty points from user account page | Mariam Nesiem