## Revisison_History
Revised on | Version | Description | Revised by
28/4/2019 | 0 | Document Created | Marwa sheshtawy
29/4/2019 | 1 | Peer Reviewed and some comments added | Aya Hamdy

## Risk_Sheet_V1
Risk ID | Risk Description | impact | Mitigation Option | Mitigation option description | Risk Type
Risk_001 | Delivery Timing within only 1 month | Medium | Mitigate | 1- Working more than 8 hours per day. 2- Working during weekends. 3- Team's workload is divided fairly | Project
Risk_002 | Scope Change , all project work products are usually designed based on the initial project scope. Thus, any change in the project scope during execution will mean that the entire initial project plan will have to be reviewed | High | Mitigate | More time and resources will be needed as all the concerned parties need to work on the new scope or modify their previous work. | Project
Risk_003 | Ramadan Working hours - Fasting in the summer, combined with disturbances in normal sleep pattern, can leave individuals feeling more tired than normal and potentially light headed | Medium | Accept | Accommodating flexible working hours , No need for face - to - face meetings , using Video Conferencing Apps for Virtual Meetings is enough like (Skype) or desktop sharing Apps like (Team Viewer) . | Project
Risk_004 | Lack of JavaScript, bootstrap knowledge by most of the team | Low | Mitigate | Work on developing the team skills during requirement analysis and design phase . | Product
Risk_005 | WebPage gui doesn't meet customer needs | High | Mitigate | Clear Acceptance criteria must be defined , wireframes will be developed first before designing to assure that the designs meet customer expectations. | Business
Risk_006 | Impacted individuals aren't kept informed of any changes. | Medium | Avoid | all team members must be involved in change process and any and all changes must be documented and uploaded to the CM tool. | Project
Risk_007 | The Competition between teams | Low | Accept | try to meet deadlines as much as possible , keep the whole team motivated all the time . | Project
Risk_008 | The cost of web hosting site | High | Transfer | Use free web hosting for 3 months then Transfer to one of Enterprise track to get the best web hosting services . | Business
Risk_009 | Integration of tasks | Low | Mitigate | daily meeting ( not necessarily face to face meeting) to integrate and communicate the tasks done by each team member at the end of the day | Product
Risk_010 | Integration of tasks | Low | Mitigate | daily meeting ( not necessarily face to face meeting) to integrate and communicate the tasks done by each team member at the end of the day | Product
Risk_011 | Delays to stakeholder approvals impact the project | Medium | Avoid | By sending to stakeholder as early as possible and send questions with proposed solution to facilitate the speed answering . | Business

## Risk_Sheet_PR
RISK ID | Revised on | Version | Description | Notes | Reviewed By
Risk_004 | 29/4/2019 | 1.1 | Lack of JavaScript, bootstrap knowledge by most of the team | * Lack of development knowledge by most of the team | Aya Hamdy
Risk_004 | 29/4/2019 | 1.1 | Work on developing the team skills during requirement analysis and design phase . | * Work on team skills development during requirement analysis and design phase . | Aya Hamdy
Risk_006 | 29/4/2019 | 1.1 | all team members must be involved in change process and any and all changes must be documented and uploaded to the CM tool. | all team members must be involved in any change process, all changes must be documented and uploaded to the CM tool. | Aya Hamdy
1.1
1.1
1.1
1.1