## Foodie_IssuesSheet_ُExternal
Issues List
ID | Description | Corrective Action | Start Day | End Day | Status
Foodie_IS_Ext_001 | Sunday and Monday were holidays so we couldn't make any meetings or work | working more hours during the week | 2019-04-28 |  | Open
Foodie_IS_Ext_002 | Configuration management tool misconfiguration, lead to loss of files | re-configuring the repository using local copies of the files | 2019-05-01 | 2019-04-29 | Closed
Foodie_IS_Ext_003 | answers to the SIQ sheet that was sent by the customer came late | working more hours during the week | 2019-05-02 | 2019-05-03 | Closed
Foodie_IS_Ext_004 | Decisions made on the project lifecycle changed multiple times | several amendments to different types of documents were made | 2019-04-29 | 2019-05-02 | Closed
Foodie_IS_Ext_005 | versioning and naming conventions were not well planned | team held a meeting to decide on a naming convention | 2019-05-03 |  | Open

## Foodie_IssuesSheet_ُInternal
Issues List
ID | Description | Corrective Action | Start Day | End Day | Status
Foodie_IS_Int_001 | IDs in the RTM sheet are not logically sequenced | - | 2019-05-04 |  | Open
Foodie_IS_Int_002 | Requirements in the SRS Document need grammar revision |  | 2019-05-04 |  | Open
Foodie_IS_Int_003 | Possible conflict between req "Foodies_SRS_037" and "Foodies_SRS_040", the 2 requirements should be merged |  | 2019-05-04 |  | Open
Foodie_IS_Int_004 | Security testing should be written in the out of scope section in the project plan | Security testing added in the out of scope section in the test plan document | 2019-05-04 | 2019-05-04 | Closed
Foodie_IS_Int_005 | User manual was not suggested to the customer in the SIQ | user manual will be written at the end of the implementation phase | 2019-05-04 | 2019-05-10 | Closed
Foodie_IS_Int_006 | Project plan doesn't have an "Objectives" Section |  | 2019-05-04 |  | Open
Foodie_IS_Int_007 | "Deliverables from client" Section should be removed from the project plan document | "Deliverables from client" removed from the project plan document | 2019-05-04 | 2019-05-08 | Closed
Foodie_IS_Int_008 | integration of tasks was not detailed enough |  | 2019-05-04 |  | Open
Foodie_IS_Int_009 | Naming convention for baselines was not well implemented | naming convention is done using github "tags and releases" | 2019-05-04 | 2019-05-05 | Closed
Foodie_IS_Int_010 | Baseline strategy is missing from Configuration Management Plan |  | 2019-05-04 |  | Open

## Revision History
External Issues Sheet (Can be sent to client) |  |  |  | Internal Issues Sheet (For internal use)
Version | Description | Author | Reviewed By | Version | Description | Author | Reviewed By
1 | Initial creation | Aya Hamdy | Maryam M. | 1 | Findings by QA Team (Mohammed Hassan) | Maryam M.