## RTM
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## SRS
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## SIQ
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## RiskSheet
RISK ID | Revised on | Version | Description | Notes | Reviewed By
Risk_004 | 29/4/2019 | 1.1 | Lack of JavaScript, bootstrap knowledge by most of the team | * Lack of development knowledge by most of the team | Aya Hamdy
Risk_004 | 29/4/2019 | 1.1 | Work on developing the team skills during requirement analysis and design phase . | * Work on team skills development during requirement analysis and design phase . | Aya Hamdy
Risk_006 | 29/4/2019 | 1.1 | all team members must be involved in change process and any and all changes must be documented and uploaded to the CM tool. | * all team members must be involved in any change process, all changes must be documented and uploaded to the CM tool. | Aya Hamdy
Risk_007 | 2019-02-05 | 1.2 | Use free web hosting for 3 months then Transfer to one of Enterprise track to get the best web hosting services . | * I think as a learning project 3 months is enough for free hosting, if we host our web application | Aya Hamdy
Risk_009 | 2019-02-05 | 1.2 | Integration of tasks | * this is a high impact because our lack of development with web backend languages, so the integration will be high risky to our team | Aya Hamdy
Risk_010 | 2019-02-05 | 1.2 | Integration of tasks | * duplicate with Risk_009 | Aya Hamdy
Risk_011 | 2019-02-05 | 1.2 | Delays to stakeholder approvals impact the project | * I think it has a high impact beacuase we send to our customer early and he delay with the answer | Aya Hamdy
All Risks | 2019-02-05 | 1.2 |  | ALL risks shoud be prioritized. | Aya Hamdy

## RACI
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CRS
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CMP
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CI List
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## TestPlan
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## PP
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CCB
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CR
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## DefectReport
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## TestCaseReport
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## IssuesList
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## SDD
ID | Document ID | Document Version | Notes | Reviewer Name | Status | publisher notes | Date of finding | Date of Solving
PR_SDD_001 | Foodies_Sys_UseCase_001 | 1.5 | confirmation password is missing at steps number 2 | Mariam Nesiem | Fixed |  | 2019-09-05 | 2019-10-05
PR_SDD_002 | Foodies_Sys_UseCase_001 | 1.5 | step number 4 from steps : system should return to home page not login page | Mariam Nesiem | Fixed |  | 2019-09-05 | 2019-10-05
PR_SDD_003 | Foodies_Sys_UseCase_002 | 1.5 | step number 3.1 from steps : if user is an admin should be redirected to admin panel not profiles page | Mariam Nesiem | Fixed |  | 2019-09-05 | 2019-10-05
PR_SDD_004 | Foodies_Sys_UseCase_003 | 1.5 | step number 1 from steps : user can show loyalty points from user account page | Mariam Nesiem | Fixed |  | 2019-09-05 | 2019-10-05