## Revision_History
Revised on | Version | Description | Author | Reviewed By | Date of Question | Date of Answer
28/4/2019 | 0.1 | Intial SIQ Creation | Hossam Galal
28/4/2019 | 0.1 | Review Document , modify some questions and solutions for clarity | Hossam Galal | Marwa Sheshtawy
28/4/2019 | 1.2 | Updated documents for the SIQ after review | Hossam Galal
28/4/2019 | 1.2 | Review Document , modify some gramatically and spelling mistakes | Hossam Galal | Aya Hamdy
29/4/2018 | 1.2 | Add customer Answers and solutions , delete an empty row | Hossam Galal | Aya Hamdy
| 1.3 | Change the SIQ ID and CRS ID | Hossam Galal | Marwa Sheshtawy
| 1.3 | add new SIQ questions | Hossam Galal | Aya Hamdy
| 1.4 | add new SIQ questions | Aya Hamdy
| 1.5 | add new SIQ questions | Aya Hamdy | Mariam Nesim | 2019-12-05
| 1.6 | add new SIQ questions | Aya Hamdy |  | 13/5/2019

## SIQ_V1
Customer Requirment | ID | Questions | proposed Solutions | Status | Date of Question | Date of Answer
| Foodies_SIQ_001 | What are the supported languages ? | English / Franko | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_001 | Foodies_SIQ_002 | What is the Characteristics of Strong Password ? | Length - Minimum [8] Maximum [10] Accepts Alphanumeric and Special Character. Must have 2 Capital letters. | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_001 | Foodies_SIQ_003 | Rigestration form with email and password Only ? | Add Conifrmation password field Add UserID - Length - Minimum [4] Maximium [8] UserID Accept Alphanumeric UserID Must be uniqe for each user | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_001 | Foodies_SIQ_004 | What's the main Content of the login page ? | UserID field Password field login BUTTON Register now LINK | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_001 | Foodies_SIQ_005 | Do you prefer the existence of alert message that inform the user that the system will access his location ? | Show an alert with yes or no should exist to ask user if it's allowed for the system to acces his location or not | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_001 | Foodies_SIQ_006 | What are the Characteristics of Valid Email ? | Email must be like this EX : Chars@Chars.com | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_001 | Foodies_SIQ_007 | Does the login Page contains Forget password and remember me functionality? | Descope | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_001 | Foodies_SIQ_008 | Shall the user will be able to register with Facebook / Gmail ? | Descope | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_001 | Foodies_SIQ_009 | Shall we include SQL injection in the scope ? | Descope |  | 28/4/2019 | 29/4/2019
Foodies_CR_002 | Foodies_SIQ_010 | Which technique used to select nearby location ? | GPS | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_002 | Foodies_SIQ_011 | what's the accepted distance between the user and the nearby restaurants? | 5KM | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_002 | Foodies_SIQ_012 | How the nearby restaurants list will be presented ? | Restaurants will be sorted aphabetically. Only five restaurants per page | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_002 | Foodies_SIQ_013 | Shall we add Next / Pervious Buttons for navigation | Add next Button for the pervious page Add next / pervious for the other pages | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_002 | Foodies_SIQ_014 | What if No nearby restaurants found ? | Display a message "There is no restaurants found". | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_002 | Foodies_SIQ_015 | what if the user wants to search in the resulted restaurants? Shall he exaclty wirte the restaurant name of substring of it ? | Exact search (write the complete name of the restaurant as it is ) | Make it substring | 28/4/2019 | 29/4/2019
Foodies_CR_003 | Foodies_SIQ_016 | Where shall the user find the promos ? | At the head of the main screen in a navigation bar link once you click on the link it show a screen with all the restaurants have a promos nearby | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_004 | Foodies_SIQ_017 | How many points the user shall get it per order ? | Every 5 orders the user will get only one order free | Approved | 28/4/2019 | 29/4/2019
Foodies_CR_004 | Foodies_SIQ_018 | What is the behaviour for show balance button ? | It calculate how many orders you need to have to free order | Not-Approved / that feature will be displayed on user account page | 28/4/2019 | 29/4/2019
| Foodies_SIQ_019 | What is the Admin features needed ? | Delete Users Add restaurants Content | Approved | 28/4/2019 | 29/4/2019
| Foodies_SIQ_020 | What is the main content for user account page ? Where I can find it ? | Picture of user UserID loyality points All users info entered in Regestration | Approved | 28/4/2019 | 29/4/2019
| Foodies_SIQ_021 | What is the first page for the application ? | login page | Approved | 2019-02-05 | 2019-03-05
| Foodies_SIQ_022 | What is the main content of delete users page ? | Search bar UserID field Search button Clear button Delete button | Approved | 2019-02-05 | 2019-03-05
| Foodies_SIQ_023 | What is the content of add resturants form and constraints ? | Name of restaurants Location Menu phone number | Approved | 2019-02-05 | 2019-03-05
Foodies_CR_002 | Foodies_SIQ_024 | What is the behaviour for making new order ? | Show a popup message contain restaurants phone number | Approved | 2019-02-05 | 2019-03-05
| Foodies_SIQ_025 | What if the admin tried to add restaurant already exist in the database? | Show a popup message says "this restaurant already added before " | Approved | 2019-02-05 | 2019-03-05
Foodies_CR_001 | Foodies_SIQ_026 | If we enter incorrect data or let the field empty what will happen? | "Please Enter Valid Data"/Next to Field | Approved | 2019-02-05 | 2019-03-05
Foodies_CR_002 | Foodies_SIQ_027 | Search bar exist in all pages or in specific page | in home page only | Approved | 2019-02-05 | 2019-03-05
Foodies_CR_004 | Foodies_SIQ_028 | How can I validate that the user already made an order ? | 1- once the popup message appears to show restaurant phone number 2- there is a submit button to confirm the order for the user 3- the admin will receive the order then have to confirm it | That will be validated from restaurant side | 2019-08-05 | 2019-10-05
| Foodies_SIQ_029 | Do you have any specific color for the web |  | Grey | 2019-08-05 | 2019-10-05
| Foodies_SIQ_030 | What is the main component of User Account page | Wireframe link: https://drive.google.com/file/d/1iuOV7VGOvl-UyZxjyO-HluDh0iEzAzGr/view?usp=sharing | Approved | 2019-08-05 | 2019-10-05
| Foodies_SIQ_031 | What is the main component of Foodies Offers page | Wireframe link: https://drive.google.com/file/d/1gsWuqykxf9sIFTrjRmh7oK8PQPnuC7sj/view?usp=sharing | Approved | 2019-08-05 | 2019-10-05
| Foodies_SIQ_032 | What is the main component of Foodies Menu page | Wireframes link: https://drive.google.com/file/d/1mFlo0tRyuSsPZtrmT5FiR-p1oy2uo8aM/view?usp=sharing | Make that to fit the browser window size | 2019-08-05 | 2019-10-05
| Foodies_SIQ_033 | What is the main component of Foodies registeration page | Wireframes link: https://drive.google.com/file/d/1Hzr_da9o8VwgI9GXJ_hq9qoAWlFp20-D/view?usp=sharing | Approved | 2019-08-05 | 2019-10-05
| Foodies_SIQ_034 | What is the main component of Foodies Home page | Wireframes link: https://drive.google.com/file/d/1_lH6wj0JQmPQdMx0iKAB28diIulHPQsS/view?usp=sharing | Approved | 2019-08-05 | 2019-10-05
| Foodies_SIQ_035 | What is the main component of Foodies Create Account page | Wireframes link: https://drive.google.com/file/d/1QqBLjckL380yHZQ7DbgMGJxgIjs_fNTK/view?usp=sharing | Approved | 2019-08-05 | 2019-10-05
| Foodies_SIQ_036 | What is the main component of Foodies Admin delete user page | Wireframes link: https://drive.google.com/file/d/1l0rqkxnki0UBwAqyxb-o4SdgGf2JqRGY/view?usp=sharing | Approved | 2019-08-05 | 2019-10-05
| Foodies_SIQ_037 | What is the main component of Foodies Add menu page | wireframes link: https://drive.google.com/file/d/1rv9v7aWvDIU2neiLoeLXTBrUPpu9JAdJ/view?usp=sharing | Make that to fit the browser window size | 2019-08-05 | 2019-10-05
Foodies_CR_004 | Foodies_SIQ_038 | How can I validate that the user already made an order ? And get the free one | 1- once the popup message appears to show restaurant phone number 2- there is a submit button to confirm the order for the user 3- after 5 orders there is a popup message says "congratulations you have one free order" Wireframe link: https://drive.google.com/file/d/1KzwfpeAiTzIihK0yYsuOOpSJByjrY4Y7/view?usp=sharing |  | 2019-12-05
| Foodies_SIQ_039 | what is the functionality of cancel button in the Signup page? | if the user decide he won't to create new account this button will redirect him/her to the login page. WireFrame link: https://drive.google.com/open?id=1Vc1-xMd-m9OSbKevYV7fuXRPwz3Hdwq2 |  | 2019-12-05
| Foodies_SIQ_040 | What is the main component of User Account page | Wireframe link: https://drive.google.com/file/d/1Ad3UcZ4IVkR51cSXja-_AtZdVZn5hfbi/view?usp=sharing |  | 2019-12-05
| Foodies_SIQ_041 | What is the main component of Foodies Offers and poromotions page | Wireframe link: https://drive.google.com/file/d/1nRW_LXT39mLwMyRpxR8DTsDkPn8gCB5k/view?usp=sharing |  | 2019-12-05
| Foodies_SIQ_042 | What is the main component of Foodies Home page | Wireframes link: https://drive.google.com/file/d/11mGrtQi1pEpCFjOHpRDiLSWV74wZK8ZF/view?usp=sharing |  | 2019-12-05
| Foodies_SIQ_043 | What is the main component of Foodies Create Account page | Wireframes link: https://drive.google.com/file/d/1QqBLjckL380yHZQ7DbgMGJxgIjs_fNTK/view?usp=sharing |  | 2019-12-05
| Foodies_SIQ_044 | What is the main component of Foodies Admin delete user page | Wireframes link: https://drive.google.com/file/d/1l0rqkxnki0UBwAqyxb-o4SdgGf2JqRGY/view?usp=sharing -- https://drive.google.com/file/d/13-tdYtyR8EnBL9Zv4n6WymFsnc6-DKmm/view?usp=sharing |  | 2019-12-05
| Foodies_SIQ_045 | what is the functionality of cancel button in the Admin delete user page? | this clear the search results if the admin decide not to delete this user |  | 2019-12-05
| Foodies_SIQ_046 | What is the main component of Foodies Admin Add resturant menu page? | * All fields are mandatory except item and promotion fields wireframes link: https://drive.google.com/file/d/1KJ6SFEyINrwY-_QW2-WvLV2VjB7wz6gZ/view?usp=sharing |  | 2019-12-05
| Foodies_SIQ_047 | what is the functionality of cancel button in the Add resturant menu page? | if the admin decide not to add resturant menu this button will redirect him/her to his/her account page |  | 2019-12-05
| Foodies_SIQ_048 | What is the main component of Foodies Login page | wireframes link: https://drive.google.com/file/d/15CgNP_MzdY5Y6-WhdA4J3xNbRFctrsil/view?usp=sharing |  | 2019-12-05
| Foodies_SIQ_049 | What is the main component of Foodies Menu and set order page | wireframes link: https://drive.google.com/file/d/1KzwfpeAiTzIihK0yYsuOOpSJByjrY4Y7/view?usp=sharing |  | 2019-12-05
| Foodies_SIQ_050 | how can I calculate the loyalty points ? | every one order the loyalty points increase by one |  | 2019-12-05
| Foodies_SIQ_051 | after the user order five orders what about the loyalty points if he/she took the free one? | the loyalty points decreases untill reaches zero, and the free order digit increases with 1 . |  | 2019-12-05
| Foodies_SIQ_052 | what is the maximum number of loyalty points the user can get ? | 5 points |  | 2019-12-05
| Foodies_SIQ_053 | are there is a logout functionality in the system ? | the system should has a logout function in the navigation bar and it should redirect him/her to the login page |  | 2019-12-05
| Foodies_SIQ_054 | what is the locations of the resturants the user can search about it ? | the system shall hold 3 locations only (Alex, Cairo, Giza) the user shall choose only one of them when submitting his/her registeration form |  | 2019-12-05
| Foodies_SIQ_055 | what is the locations of the resturants the admin can add it ? | the system shall hold 3 locations only (Alex, Cairo, Giza) the Admin shall choose only one of them when submitting the resturant form |  | 2019-12-05
| Foodies_SIQ_056 | are the admin able to make order? | No the user only is able to make order |  | 13/5/2019
| Foodies_SIQ_057 | Each order will increase the Loyalty points by one but what if this order is free one, what will happen to the loyalty points? | the loyalty points should't increase or decrease. |  | 13/5/2019
| Foodies_SIQ_058 | what will happen when the Admin delete user ? | the system should display popup message says "user deleted successfully" |  | 13/5/2019
| Foodies_SIQ_059 | what will happen when the Admin add restuarant? | the system should display popup message says "restaurant added successfully" |  | 13/5/2019

## PeerReviewNotes
SIQ_ID | Description | Proposed Solution | Notes
SIQ_1 | in question : what are the supported languages ? | English/ Franko
SIQ_2 | in question : What is the Characteristics of Strong Password ? | *Length - Minimum [8] Maximum [10] *Accepts Alphanumeric and Special Character. * Must have 2 Capital letters.
SIQ_3 |  | * add Confirm password field * it's important to be clear about the userID , it must be unique to each user ( not included in db for another user ). * Remove make wireframes for registeration form (we'll support this wireframes in design phase ).
SIQ_4 | in question : what's the main content of …. | *I think he only mentioned that login will be with UserID email will be used in forget password ?? * clearly mention that userID and password will be text Field as you mentioned that registernow will be link and so on .
SIQ_5 | Do you prefer the existence of alert message that inform the user that the system will access his location ? | an alert with yes and no should exist to ask user if it's allowed for the system to acces his location or not
SIQ_6 | what are
SIQ_7
SIQ_8 | shall the user will be able to register with …
SIQ_10 | what's the accepted distance between the user and the nearby restaurants ? | 5KM not 5000 km
SIQ_11 , SIQ_12 | How the nearby restaurants list will be presented ? | * restaurants will be sorted aphabetically. * only five restaurants per page | replace both questions with this
SIQ_13 | what if No nearby restaurants found ? | display a message "There was no restaurants found".
SIQ_14 | what if the user want to search in the resulted restaurants ? Shall he exaclty wirte the restaurant name of substring of it ? | Exact search (write th ecomplete name of the restaurants as it is )
SIQ_18 |  | restaurants
Foodies_SIQ_025 | if we enter incorrect data or let the field empty what will happen? | text message in red color appears next or under the field | "Please Enter Valid Data"/Next to Field | Please add in SIQ sheet
Foodies_SIQ_026 | search bar exist in all pages or in specific page | in home page only | Approved | Please add in SIQ sheet