## RTM
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## SRS
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## SIQ
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## RiskSheet
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## RACI
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CRS
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CMP
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CI List
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## TestPlan
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## PP
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CCB
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## CR
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## DefectReport
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## TestCaseReport
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## IssuesList
ID | Document ID | Document Version | Notes | Reviewer Name | publisher notes

## SDD
ID | Document ID | Document Version | Notes | Reviewer Name | Status | publisher notes | Date of finding | Date of Solving
PR_SDD_001 | Foodies_Sys_UseCase_001 | 1.5 | confirmation password is missing at steps number 2 | Mariam Nesiem | Fixed |  | 2019-09-05 | 2019-10-05
PR_SDD_002 | Foodies_Sys_UseCase_001 | 1.5 | step number 4 from steps : system should return to home page not login page | Mariam Nesiem | Fixed |  | 2019-09-05 | 2019-10-05
PR_SDD_003 | Foodies_Sys_UseCase_002 | 1.5 | step number 3.1 from steps : if user is an admin should be redirected to admin panel not profiles page | Mariam Nesiem | Fixed |  | 2019-09-05 | 2019-10-05
PR_SDD_004 | Foodies_Sys_UseCase_003 | 1.5 | step number 1 from steps : user can show loyalty points from user account page | Mariam Nesiem | Fixed |  | 2019-09-05 | 2019-10-05